## Eng Weekly report
Weekly Summary Report
Shaft | Nchwaning 2 | [6 empty] | Plan YTD | Actual YTD | Plan MTD | Actual MTD | Variance
[7 empty] | ROM | 721261 | 628129 | 26713 | 24466 | -2247
Week - Date to | 2025-11-28 | 2025-12-04 |  |  |  |  | Product | 660801 | 608131 | 21818 | 17186 | -4632
Safety
| YTD | No wk | Remarks
MTC | 1 | 1 | Employee slipped and fell while descending steps from Mechanics tea room
LTI | 0 | 0
PD | 5 | 0 | FL114 bumped against DT157
Incidents Reported | 0 | 0
Labour
| Plan | Actual | Leave | Not Specified | % AT Work |  | Remarks
Fri | 215 | 131 | 78 | 6 | 60.93%
Mon | 215 | 163 | 34 | 18 | 75.81%
Tue | 215 | 171 | 23 | 21 | 79.53%
Wed | 215 | 172 | 23 | 20 | 80%
Thur | 215 | 173 | 19 | 23 | 80.47%
Sat |  |  |  | 0 | #DIV/0!
Sun |  |  |  | 0 | #DIV/0!
Cost
COST By ELEMENT | MONTH ACTUAL | MONTH BUDGET | MONTH VAR | YTD ACTUAL | YTD BUDGET | YTD VAR | Remarks
Labour Cost | 13545915.37 | 13407699.97 | -138215.4 | 66479114.46 | 67482151.92 | 1003037.46
Overtime | 1082582.1 | 787163.23 | -295418.87 | 5926125.96 | 3935816.15 | -1990309.81
Incentive Provision | 2262957.49 | 2262957.49 | 0 | 958243.77 | 11314787.45 | 10356543.68
Stores | 5986897.01 | 7130561.5 | 1143664.49 | 31789553.35 | 37708465.5 | 5918912.15
Major Repairs | 2902533.12 | 3767889.76 | 865356.64 | 19422762.96 | 19411921.52 | -10841.44
Contractors | 1613947.03 | 1848208.8 | 234261.77 | 6139422.84 | 9194556.69 | 3055133.85
Other Cost | 98190.14 | 225133 | 126942.86 | 775716.06 | 1204667.5 | 428951.44
TOTAL | 27493022.26 | 29429613.75 | 1936591.49 | 131490939.4 | 150252366.73 | 18761427.33
Planned Weekend/Public Holiday Work
Description |  |  |  |  | Done | Not Done | Remarks
Drills - Support production; Service HD63 and HD64
Mechanics - Support production; DT128 transmission
Plant - production
Utility - Production and UV123 maintenance
Boilermaker - maintenance at 2West feeder discharge chute and crusher scalping screen
Electricians - Support production and remove MS007 at Main Drive and connect new minisub at 74W
Strata - Support production and CAS L9
Nerospec - Support production and CAS L9
| Fri | Mon | Tue | Wed | Thur | Average
DT | 55% | 53% | 57% | 68% | 81% | 62.8% | DT128 transmission; DT121 gears; DT159 ECM
FL | 73% | 57% | 64% | 76% | 61% | 66.2% | FL86 brakes; FL102 axle; FL106 fire suppression
HD | 97% | 87% | 83% | 90% | 92% | 89.8%
RT | 99% | 90% | 94% | 86% | 98% | 93.4%
SR | 81% | 97% | 99% | 93% | 88% | 91.6%
TMM Status SOS (Friday Morning) : | [12 empty] | 5042
Plan
HD | 6 | 6
RT | 6 | 6
DT | 9 | 8 | DT128 transmission
FL | 6 | 6 | FL86 brakes; FL102 axle; FL87 modules
SR | 6 | 5 | SR45 tyre
Charge up UV`s | 3 | 3
RORO/Flat deck UV`s | 3 | 3
Weekly Primary TMM Maintenance Overview
Challenges

## Compliance report
Weekly Asset Care Compliance Report
Don’t change Formula's
| Week Ending | 2025-12-04
| Shaft / Area | NCHW II UG
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Unit late for service (y/n) | Unit book back on time after service(y/n) |  | Week-end Service | Reasons for Non-Compliance
| DT | 2 | 2 | 100% | 100% |  | y
| FL | 3 | 3 | 100% | 100% |  | n |  |  | FL0087 After service strata replaced flasher from, mudule error
| HD | 4 | 3 | 75% | 100% |  |  |  |  | HD0063 service weekend
| RT | 2 | 2 | 100% | 100%
| SR - Service Compliance | 1 | 1 | 100% | 100%
| Support Equipment | 8 | 8 | 100% | 100%
| SR - Weekly Inspection | 8 | 8 | 100% | 100%
Service Pre-Inspection
| Fleet / Equipment | Planned | Actual | Schedule Compliance | Target | Work order number | Remarks
| DT | 0 |  |  | 95%
| FL | 1 | 1 | 100% | 95%
| HD | 3 | 3 | 100% | 95%
| RT | 3 | 3 | 100% | 95%
| SR - Service Compliance | 2 | 2 | 100% | 95%
| Support Equipment | 2 | 2 | 100% | 95%
Condition monitoring / Oil samples
| Fleet / Equipment | Engine - Plan | Engine- Received | Transmission - Plan | Transmission - Receive | Axle - plan | Axle - Receive | % Compliance | Reasons for Non-Compliance |  |  | Paperwork Correct | Paperwork Incorrect | Urgent Oil Samples | Workorder Generated
| DT | 2 | 2 | 2 |  |  |  | 50% | [5 empty] | 0
| FL | 3 | 3 | 3 |  |  |  | 50% | [5 empty] | 0
| HD | 0 | [11 empty] | 0
| RT | 0 | [11 empty] | 0
| SR | 1 | 1 |  |  |  |  | 100% | [5 empty] | 0
| Support Equipment | 8 | 8 |  |  |  |  | 100% | [5 empty] | 0
Remember Readings
Oil Filtration
| Equipment nr | Oil Type | Start Reading | End Reading | Comments |  | ISO Standard
FA0007
FA0001
| Inspection done by: | Planned Over-Inspections | Total Number of Inspections Completed | Corrective Work | Wo Number | % Completed | Remarks for not comply
| UTILITY FOREMAN | 4 | 4 |  |  | 100%
| MECHANIC FOREMAN | 5 | 5 |  |  | 100%
| DRILLS FOREMAN | 6 | 6 |  |  | 100%
| Engineer | 1 | 1 |  |  | 100%
| Electrical Foreman | 4 | 4 |  |  | 100%
| Plant Foreman | 4 | 4 |  |  | 100%
| GES Plant | 1 | 1 |  |  | 100%
| GES TMM | 1 | 1 |  |  | 100%
| Equipment ID | Date of Inspection | Inspection Performed by | Findings and Defects Completed |  |  | Additional Follow-up Work |  |  | WO No. | Status
| Conveyor belt guard inspection | 01/12/2025 | Lebogang | None |  |  | None |  |  | 1884095
| Beltspray & firehose inspection | 02/12/2025 | Lebogang | None |  |  | None |  |  | 1884100
| Workshop Housekeeping | 03/12/2025 | Lebogang | None |  |  | None |  |  | 1885247
| U/G pump over inspection | 04/12/2025 | Lebogang | None |  |  | None |  |  | 1881614
| FL0100 | 17/11/2025 | GAE | Repair oil leak | [5 empty] | 1883436
| FL0120 | 28/11/2025 | GAE | [6 empty] | 1887513
| DT0120 | 01/12/2025 | GAE | grease system | [5 empty] | 1874265
| DT0158 | 02/12/2025 | GAE | [6 empty] | 1880718
| FL0102 | 03/12/2025 | GAE |  |  |  | REPLACE FRONT AXLE |  |  | 1853836
| FL0087 | 04/12/2025 | GAE |  |  |  | CAN COMMUNICATION ERROR
| LDO633 | 26/11/2025 | DUBA | None |  |  | None |  |  | 1887516
| LD0580 | 01/12/2025 | DUBA | None |  |  | None |  |  | 1887516
| SR0045 | 01/12/2025 | DUBA | None |  |  | None |  |  | 1896498
| LD0605 | 03/12/2025 | DUBA | None |  |  | None |  |  | 1893074
| UV0119 | 04/12/2025 | DUBA | None |  |  | None |  |  | 1853835
| UV0123 | 05/12/2025 | DUBA | None |  |  | None |  |  | 1883443
| LD0579 | 05/12/2025 | DUBA | None |  |  | None |  |  | 1880723
| LD0590 | 05/12/2025 | DUBA | None |  |  | None |  |  | 1889543
| RT0038 | 28/11/2025 | ROY | None |  |  | None |  |  | 1884454
| RT0040 | 04/12/2025 | ROY | Leaking eingine oil cooler |  |  | Repariared the leak |  |  | 1880763
| HD0064 | 02/12/2025 | ROY | None |  |  | None |  |  | 1882703
| HD0065 | 04/12/2025 | ROY | None |  |  | None |  |  | 1884357
| HD0068 | 05/12/2025 | ROY | Driving lights switch |  |  | Replaced the switch |  |  | 1882702
| Conv 5 | 01/12/2025 | Shaied | 3 x Lights |  |  | To be replaced |  |  | 1881812
| Conv 6 | 01/12/2025 | Shaied | 2 x lights |  |  | To be replaced |  |  | 1881813
| Conv 7 | 01/12/2025 | Shaied | None |  |  | None |  |  | 1881814
| Conv 8 | 01/12/2025 | Shaied | None |  |  | None |  |  | 1881815
I

## Quality report
Weekly Asset Care Compliance Report Nchwaning II UG
| Week Ending | 2025-12-04 | [6 empty] | NB: PLEASE DO NOT EDIT ON YELLOW COLUMN
| Shaft / Area | Nch II U/G
Weekly Quality Service Report
|  |  | Mining |  |  |  | 73.08% | Engineering | [5 empty] | 78.46%
| Schedule Date | TMM Unit Number | Actual Time Available In Workshop - < 7:00 AM | 07:00 AM - 50% 08:00 AM - 25% 09:00 AM - 0% | Machine Clean for Maintenance | No - 0% Yes - 50% |  | Pre inspection & Operator Engagement - 3 Days Before Service Done | No - 0% Yes - 25% | Actual Service Duration - Plan 6 Hours | 6Hrs - 50% 5Hrs - 40% 4Hrs - 30% 3Hrs - 20% 2Hrs - 10% 1Hrs - 0% | Machine Tested and Over Inspected by Supervisor | No - 0% Yes - 25% |  | Completed Service Workorder number | Actual Hrs on service date
1 | 2025-11-28 | DT0158 | 19:00 | 25% | Yes | 50% | 75% | Yes | 25% | 3hrs | 20% | Yes | 25% | 70%
2 | 2025-11-28 | LD0579 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
3 | 2025-12-01 | DT0120 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
4 | 2025-12-01 | HD0063 |  |  |  |  | 0% | [6 empty] | 0%
5 | 2025-12-01 | RT0038 | 08h00 | 50% | Yes | 50% | 100% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
6 | 2025-12-01 | SR0045 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
7 | 2025-12-01 | LD0580 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
8 | 2025-12-02 | FL0100 | 14:00 | 25% | Yes | 50% | 75% | Yes | 25% | 3hrs | 20% | Yes | 25% | 70%
9 | 2025-12-02 | HD0064 | 08h00 | 25% | Yes | 50% | 75% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
10 | 2025-12-02 | UV0137 |  |  |  |  | 0% | [6 empty] | 0%
11 | 2025-12-02 | LD0590 | 7:00 | 50% | Yes | 50% | 100% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
12 | 2025-12-03 | FL0102 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
13 | 2025-12-03 | HD0065 | 8h00 | 50% | Yes | 50% | 100% | Yes | 25% | 6hrs | 50% | Yes | 25% | 100%
14 | 2025-12-03 | UV0119 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
15 | 2025-12-03 | LD0605 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
16 | 2025-12-04 | FL0087 |  |  |  |  | 0% | [6 empty] | 0%
17 | 2025-12-04 | RT0040 | 09h00 | 0% | Yes | 50% | 50% | Yes | 25% | 5hrs | 40% | Yes | 25% | 90%
18 | 2025-12-04 | UV0123 | 7:00 | 50% | Yes | 50% | 0% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
19 | 2025-12-04 | LD0633 | 8:00 | 25% | Yes | 50% | 75% | Yes | 25% | 6Hrs | 50% | Yes | 25% | 100%
20 | [6 empty] | 0% | [6 empty] | 0%
21 | [6 empty] | 0% | [6 empty] | 0%
22 | [6 empty] | 0% | [6 empty] | 0%
23 | [6 empty] | 0% | [6 empty] | 0%
24 | [6 empty] | 0% | [6 empty] | 0%
25 | [6 empty] | 0% | [6 empty] | 0%
26 | [6 empty] | 0% | [6 empty] | 0%
27 | [6 empty] | 0% | [6 empty] | 0%
28 | [6 empty] | 0% | [6 empty] | 0%
29 | [6 empty] | 0% | [6 empty] | 0%
30 | [6 empty] | 0% | [6 empty] | 0%
31 | [6 empty] | 0% | [6 empty] | 0%
32 | [6 empty] | 0% | [6 empty] | 0%
33 | [6 empty] | 0% | [6 empty] | 0%
34 | [6 empty] | 0% | [6 empty] | 0%

## Service schedule
Asset Care Service Compliance
| Week: | 05 - 10 Dec 2025
| 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11
Equip type | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
DT
FL
HD
RT
SR
Support
Outstanding
Compressor's
Over Inspections
FM Drill: |  |  |  | FM Mech:
FM Elect: |  |  |  | GES:
ENG: |  |  |  | MO:

## Oil report
No report from Petroman

## Fermel Weekly
N 2
No | Area / Owner | TMM Type | TMM No. | Breakdown | Comment | OEM Assistance Required |  | Utility Machine | Total | Breakdown | Availabile
| RORO UV'S FERMEL | [6 empty] | Maverick Dble Cab STD Load Bin | 11 | 3 | 72.73%
2 | BRP/Logistics | Liberator Roll On Roll Off | UV0054 |  | Available |  |  | Maverick Man Lift | 4 | 1 | 75%
3 | BRP/Logistics | Liberator Roll On Roll Off | UV0059 |  | Available |  |  | Liberator Roll On Roll Off | 6 | 2 | 66.67%
4 | Roadways | Liberator Roll On Roll Off | UV0061 |  | Available |  |  | Placer dumper | 1 | 0 | 100%
5 | BRP/Logistics | Liberator Roll On Roll Off | UV0118 | the water tank hydraulic pump is currently leaking oil from the seal face during operation. and note that this pump on the water site was previously attended to by the OEM. However, the machine has not operated effectively and has not run more than 40–100 hours since the OEM worked on the pump. We have arranged for UV118 to be driven to surface today for the OEM to attend to the issue, as the technician was experiencing difficulties with Passport 360. | Not Available |  |  | Maverick king Cab c/w Crane | 3 | 1 | 66.67%
6 | BRP/Logistics | Fermel Placer Dumper | UV0119 |  | Available |  |  | Maverick Single cab Jam Pot | 1 | 0 | 100%
7 | BRP/Logistics | Liberator Roll On Roll Off | UV0120 |  | Available |  |  | Maverick 12 Man Trooper | 3 | 1 | 66.67%
8 | BRP/Logistics | Liberator Roll On Roll Off | UV0133 | the machine is currently standing due to a faulty end play. We are still waiting parts, and in the meantime, the machine has been towed out of the way to avoid obstruction on sot production machines, | Not Available |  |  | Scaler | 8 | 0 | 100%
| MAVERICK UV'S | [6 empty] | Toyota landcuiser ambulance | 1 | 0 | 100%
10 | Williams /drill mec | Maverick King Cab NO Crane | UV0069 |  | Available |  |  | Maverick king Cab with no Crane | 2 | 1 | 50%
11 | Kal Tire | Maverick King Cab NO Crane | UV0072 | engine cu off due to a trm sensor fauly ,still busy with troubleshooting | Not Available |  |  | Toyota landcruiser | 36 | 4 | 88.89%
12 | Williams | Maverick king Cab c/w Crane | UV0087 |  | Available |  |  |  | 76 | 13 | 82.89%
13 | Fitters | Maverick king Cab c/w Crane | UV0090 | we drilled the broken pin out; still busy with assembling the front engine components. | Not Available
14 | Gae | Maverick king Cab c/w Crane | UV0092 |  | Available
15 | Sanitation | Maverick Single cab Jam Pot | UV0102 |  | Available
MAVERICK LDO'S
17 |  |  | LD0378
18 | Roadways | Maverick Dble Cab STD Load Bin | LD0407 |  | Available
19 | Williams /drill mec | Maverick Dble Cab STD Load Bin | LD0408 | The machine still on breakdown display not coming on and no ground earth busy with troubleshooting | Not Available
20 | Mining/28 section | Maverick Dble Cab STD Load Bin | LD0411 |  | Available
21 | Technicians | Maverick Dble Cab STD Load Bin | LD0414 |  | Available |  | Labour for the week including Nightshift
22 | Themba fire fighters | Maverick Dble Cab STD Load Bin | LD0415 |  | Available |  | Foreman | 1 of 1
23 | Boilermakers | Maverick Dble Cab STD Load Bin | LD0419 |  | Available |  | Chargehand | 1 of 1
24 | Technicians | Maverick Dble Cab STD Load Bin | LD0426 | During the troubleshooting following a reported engine cut-off, we discovered that the engine is mixing oil and coolant. This condition of an engine could be a cracked cylinder head or a worn head gasket.New engine will be needed | Not Available |  | Mechanics | 9 of 7 | 2 | AL,NOT AVAIL
25 | Explosive | Maverick Dble Cab STD Load Bin | LD0450 |  | Available |  | Auto Electrician | 3 of 2 |  | TT
26 | Capital graben | Maverick Dble Cab STD Load Bin | LD0508 |  | Available |  | Semi skilled | 2 of 2
27 | Gae | Maverick Dble Cab STD Load Bin | LD0509 |  | Available |  | Leaners
28 | Capital graben | Maverick Dble Cab STD Load Bin | LD0519 | the machine is currently not starting. There is no power on the start button circuit not getting power. We are busy with troubleshooting | Not Available
29
30
32
33
34
35
36
37
| MAVERICK LDO'S TROPPER | [5 empty] | DELAY:
39 | Fitters | Maverick 12 Man Trooper | LD0477 |  | Available
40 | Mining/28 section | Maverick 12 Man Trooper | LD0523 | machine was reported with starting troubleshoot on battery circuit done and found that injector one has faulty and machine misfiring | Not Available
41 | Construction | Maverick 12 Man Trooper | LD0532 |  | Available
42 | MAVERICK UV'S MANLIFTS | [5 empty] | PRIORITY FOR THE NEXT SHIFT
43 | Geologist | Maverick Man Lift | UV0077 | The machine must be moved to Fermel Head Office for refurbishment of the bucket harness and front outriggers | Not Available
44 | Survey | Maverick Man Lift | UV0098 |  | Available
45 | Survey | Maverick Man Lift | UV0099 |  | Available
46 | Geologist | Maverick Man Lift | UV0123 |  | Available |  | SERVICE UPDATES
TOYOTA CRUISER LDO'S
47 | Ambulance | Toyota Cruiser 4x4 emergency vehicle | LD0 341 |  | Available
48 | Capital graben | Toyota Cruiser 4x4/Trimming-Connie | LD0 553 | busy with level 9 upgrades | Not Available
49 | Lebolo/2west2body | Toyota Cruiser 4x4/mining -Lebelo | LD0 554 |  | Available
50 | Connie Trimming | Toyota Cruiser 4x4/Trimming-Connie | LD0 557 |  | Available
51 | Fitters w/shop | Toyota Cruiser 4x4/fitter plant-Lebogang | LD0 575 |  | Available
52 | Electrical w/shop | Toyota Cruiser 4x4 /electrician-Hansie | LD0 576 |  | Available
53 | Connie Mining | Toyota Cruiser 4x4/mining-Connie | LD0 577 |  | Available
54 | Peace | Toyota Cruiser 4x4/mining -portgter | LD0 578 | machine its out of nch 2 production and team are busy with panelbeat at blackrock | Not Available
55 | Christo | Toyota Cruiser 4x4/mining-christo | LD0 579 | nerospec and strata level 9 commissioning | Not Available
56 | Training Center | Toyota Cruiser 4x4/training center | LD0 580 |  | Available
57 | Potgieter | Toyota Cruiser 4x4/Mining 28 section | LD0 581 |  | Available
5
55
56
AARD UV'S
58 | Duba Utility | aard-uv60-diesel tank | UV0053 |  | Available
59 | Hansie Louw | aard-uv60 | UV0084 |  | Available
| Roadways | aard-uv80-water tank truck | UV0121 |  | Available
61 | Capital-Graben | aard-uv80 | UV0130 |  | Available
62 | Construction | aard-uv60 | UV0139 |  | Available
63 | Construction | aard-uv60 | UV0140 |  | Available
64 | Capital-Graben | aard-uv80 | UV0130 |  | Available
65 | Construction | aard-uv60 | UV0139 |  | Available
66 | Construction | aard-uv60 | UV0140 |  | Available
67 |  |  |  |  | Available
68
| SCALER'S |  |  |  | Available
70 | Scaler | Scaler | SR0025 |  | Available
71 | Scaler | scaler | SR0027 |  | Available
72 | Scaler | Scaler | SR0029 |  | Available
73 | Scaler | Scaler | SR0033 |  | Available
74 | Scaler | scaler graben Capital Tel 5013 | SR0036 |  | Available
75 | Scaler | scaler 17upper 74 Portigter | SR0042 |  | Available
76 | Scaler | scaler 17upper 74 Portigter | SR0045 |  | Available
77 | Scaler | scaler graben Capital Tel 5013 | SR0046 |  | Available
| Scaler | Scaler Mining | SR0053 |  | Available
78 | Scaler | Scaler Mining | SR0054 |  | Available
TOYOTA CRUISER WITH HIAB'S
78 | Life Tmm | Toyota Cruiser 4x4 | LD0 589* |  | Available
79 | Duba Utility | Toyota Cruiser 4x4 | LD0 590* |  | Available
80 | Didi-Boilermaker | Toyota Cruiser 4x | LD0 592* |  | Available
81 | Izak Bothman KalTire | Toyota Cruiser 4x4/Kal Tire | LD0 593* |  | Available
82 | Fitters Lebogang | Toyota Cruiser 4x4/ | LD0 594 |  | Available
83 | Duba Utility | Toyota Cruiser 4x4/ | LD0 621 |  | Available
84 | Life Tmm | Toyota Cruiser 4x4/ | LD0 633 | nerospec have to attand it doing upgade | Not Available
TOYOTA CRUISER TROPPER'S
84 | Karl Roadways | Toyota Cruiser 4x4/ | LD0 596 |  | Available
85 | Geologist&Survey | Toyota Cruiser 4x4/ | LD0 605 |  | Available
86 | Mining-Peace | Toyota Cruiser 4x4/ | LD0 629 |  | Available
| Mining | Toyota Cruiser 4x4/ | LD0 649 |  | Available
| Duba Utility | Toyota Cruiser 4x4/ | LD0 650 |  | Available
TOYOTA CRUISER WITHOUT HIAB'S
87 | William Tel:5429 | Toyota Cruiser 4x4/ lube | LD0 591 |  | Available
88 | Duba Utility | Toyota Cruiser 4x4- single cap | LD0 621* |  | Available
89 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0 623 |  | Available
90 | Electrician tel:5416 | Toyota Cruiser 4x4/ | LD0630* |  | Available
91 | William Tel:5429 | Toyota Cruiser 4x4/ | LD0631 |  | Available
92 | Boilers | Toyota Cruiser 4x4 | LD0634* |  | Available
93 | Izak Botham | Toyota Cruiser 4x4/ drill rod carrier | LD0636* |  | Available
| Manyafunyafu | CRUISER SINGLE CAP Hiab | LD0642 |  | Available
| William Tel:5429 | CRUISER SINGLE CAP Hiab | LD0647 |  | Available
| Life Tmm | CRUISER SINGLE CAP Hiab | LD0648 |  | Available
| Strata team | CRUISER SINGLE CAP Hiab | LD0658 |  | Available
| Project | CRUISER 8 Seater | LD0675 |  | Available

## Blocked chutes
0 | Details | FEEDER BELT CHUTE |  |  | TIPS 1&2 | [5 empty] | Area xyz
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
01/12/2025 | Reason for blockage | Big rock wedge | No blockages | No Blockage | No Blockage | No blockages | No blockage | No Blockage | No blockages | No Blockage
| Time of blockage | 12h37-13h02 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
02/12/2025 | Reason for blockage | No Blockage | No blockages | No Blockage | No Blockage | No blockages | No blockage | No Blockage | No blockages | No Blockage
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba | J Benson | TK Mosiane | Xaba
03/12/2025 | Reason for blockage | No Blockage | No blockages | No Blockage | No Blockage | No blockages | No blockage | No Blockage | No blockages | No Blockage
| Time of blockage | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
| Supervisor/artisan who assisted with unblocking | J Benson |  | Xaba | J Benson |  | Xaba | J Benson |  | Xaba
04/12/2025 | Reason for blockage | Big rock wedge inside chute |  | No Blockage | No Blockage |  | No blockage | No Blockage |  | No Blockage
| Time of blockage | 11h16-11h37 |  | N/A | N/A |  | N/A | N/A |  | N/A
Supervisor/artisan who assisted with unblocking
05/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
06/12/2026 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
07/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
08/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
09/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
10/12/2025 | Reason for blockage
Time of blockage
11/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
12/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
13/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
14/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
15/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
16/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
17/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
18/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
19/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
20/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
21/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
22/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
23/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
24/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
25/12/2025 | Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
26/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
27/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
28/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
29/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
30/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
31/12/2025 | Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage
Supervisor/artisan who assisted with unblocking
Reason for blockage
Time of blockage